## Sheet1
EduConnect | Notes | Meeting Notes | Work | [5 empty] | 2026-06-05 |  | additional
1.0 Home Page | Good - To review dashboards | [7 empty] | added gender and learning goals | need to fix token
1.1 Survey | To test - keeps scrolling to top when choosing -Typing stopping | Learning goals - to add options Add hours to consacrate Gender choice | 2026-04-17 | [5 empty] | Next : To test - keeps scrolling to top when choosing -Typing stopping |  | Teachers can input different learning styles - to do research on that auditory,visual etc
1.2 Find My Perfect Match | To test -can be sorted into tutors and courses | [7 empty] | 2026-06-06 |  | Can be sorted according to learning style : selected learning style appears on top
2.0 Courses Page | Good Overall | Can be sorted according to learning style : selected learning style appears on top | 2026-04-16 | [5 empty] | Learning goals and gender okay Course manager fixed to fix survey data matching with tutor profile,calendar, to be enhanced |  | To test -can be sorted into tutors and courses
Price to check
3.0 My Courses | View Course Materials - To test | [7 empty] | 2026-06-07
4.0 Messages | To remove Video call replace with voice call |  | 2026-04-13 | 2026-04-14 | 2026-04-15 |  |  |  | survey fixed AI fixed | need to fix course viewer- image not working, to remove ppxt - cannot delete section nor material uploaded nor course Limited chat availability Review dashboard keyboard fixes
| To prevent duplicate of message/ Messages are not sending - duplicate fixed | Video Call not appearing
To put correct formatting and spacing of names
| React Native does not support daily api - to look for others -Webrtc | Limited chat availability - restrict chatting + voice call
5.0 Registation | To fix sizing |  | 2026-04-15 |  |  | to do | to do | to do
5.1 login | fix not being able to type
5.2 UI | Fix
6.0 Home Page | Good - To review dashboards
7.0 Course Manager | To review category |  | 2026-04-16 |  |  | to do | to do | to do
To fix UI
Teachers can input different learning styles - to do research on that auditory,visual etc
Publish option can be free or payable
8.0 Profile | + |  | 2026-04-15
Email validation in database
9.0 Notifications |  |  | 2026-04-18
+

## Testing
Profile | Module | Test Scenarios | Stage
Student | Profile